MATER DEI COLLEGE

College of Arts, Sciences and Technology (CAST)

INTERNTRACK

Internship Journal and Progress Monitoring System

DEVELOPMENT ROADMAP

Monorepo Build Plan — Backend API · Web Portal · Mobile App

| Group | Group 1 |
| --- | --- |
| Members | Aleria, Mark Lloyd L. · Mar, John Carlo S. · Pelesories, Reggie Niño Z. · Sapid, Lenny B. |
| Architecture | Laravel 13 API (backend) · Vue 3 SPA (web) · React Native / Expo (mobile, student-facing) |
| Database Baseline | InternTrack_Database_Schema_v2.0 — 20 tables |
| Department Coverage | CAST (1 program) · CABM-B (4 programs) · CABM-H (2 programs) — 7 programs total |
| Document Version | v2.1 — multi-department scalability confirmed |

# How to Read This Roadmap

This roadmap sequences InternTrack's build across seven phases. Each phase lists what gets built on each part of the stack — backend (Laravel API), web (Vue 3), and mobile (React Native / Expo, student-facing only) — along with the database tables involved and the exit criteria that mark a phase as done.

Phases are sequential where there's a real dependency (you can't build the weekly review workflow before journal entries exist), but tracks within a phase can run in parallel across the three of you working on backend, web, and mobile respectively. Durations are planning estimates for a student team working part-time around other coursework — adjust based on your actual pace.

This version reflects the team's decision to delete the original repository and start the codebase from scratch, rather than restructuring the previous Laravel + Inertia.js monolith. There is no legacy code to migrate or salvage — Phase 1 below builds the monorepo directly.

Confirmed Resolved / Out of Scope Two scope questions from earlier planning are now settled. Geofence + rotating QR clock-in/out is confirmed out of scope per team decision. Exit Interview Summary (shown in an earlier HTML mockup for the Coordinator and Admin roles) is also confirmed excluded — the finalized v2.0 schema documentation explicitly notes that the exit_interview_reports table has been removed from scope per project decision. Neither feature appears anywhere in this roadmap.

# Roadmap at a Glance

| # | Phase | Duration | Primary Output |
| --- | --- | --- | --- |
| 1 | Foundation & Environment Setup | 1–2 weeks | Monorepo skeleton, Breeze API auth, all 20 tables migrated |
| 2 | Identity, Roles & Account Management | 1–2 weeks | Working login, role middleware, admin account/batch creation |
| 3 | Core Daily Journal Flow | 2–3 weeks | Students can write, edit, and track daily journal entries |
| 4 | Weekly Review Workflow | 2 weeks | Sunday auto-bundling, supervisor approve/return, edit history |
| 5 | SIPP Compliance & Reporting | 2–3 weeks | Student Info Sheet, Weekly Activity Log, Annual SIPP, PDF export |
| 6 | Notifications & Administrative Tools | 2 weeks | Email/push reminders, overdue tracking, system settings, audit log |
| 7 | Mobile Parity, Polish & Testing | 2–3 weeks | Mobile feature parity, QA pass, UAT, defense readiness |

Total estimated timeline: 12–17 weeks of active development, excluding documentation chapters (4–5), defense preparation, and revision cycles.

# PHASE 1   Foundation & Environment Setup

Suggested Duration: 1–2 weeks      Depends On: None — starting point

BACKEND (Laravel API)

- Create a new GitHub repository and initialize the backend/, web/, and mobile/ monorepo layout from scratch

- Initialize Laravel 12 project in backend/; configure .env for local MySQL (XAMPP)

- Install Laravel Breeze using the API stack: php artisan breeze:install api

- Install and configure Laravel Sanctum; set SANCTUM_STATEFUL_DOMAINS for the web SPA

- Configure CORS (config/cors.php) to allow the Vue dev server origin

- Write all 20 migrations fresh against the v2.0 schema document, in dependency order (departments → programs → users → ...)

- Run migrations against a fresh local database and confirm all foreign keys resolve without error

- Set up base model relationships (Eloquent) for every table per the Key Relationships section of the schema doc

- Create a basic database seeder for departments, programs, and a test admin user

WEB (Vue 3)

- Initialize Vue 3 project in web/ with Vite

- Install and configure Vue Router, Pinia, Axios, Tailwind CSS

- Set up the Axios instance with withCredentials for Sanctum cookie auth (final wiring deferred to login work)

- Recreate the four role-based shell layouts (sidebar nav, topbar, content area) from the HTML mockup, as static Vue components without live data yet

MOBILE (React Native / Expo — Student Only)

No mobile work this phase — nothing student-facing is ready to expose yet. Project scaffolding can proceed in parallel if convenient.

DATABASE TABLES TOUCHED

All 20 tables (schema verification only — no feature logic yet)

EXIT CRITERIA — done when:

- php artisan migrate runs clean from an empty database with zero errors

- Breeze api routes are registered and visible in php artisan route:list

- The Vue app boots locally and renders the four static role shells from the mockup

- All three members can run their respective part of the stack locally without environment errors

# PHASE 2   Identity, Roles & Account Management

Suggested Duration: 1–2 weeks      Depends On: Phase 1

Scalability confirmed — multi-department / multi-program The departments → programs schema (one department, many programs) already supports the full confirmed department coverage — CAST (1 program), CABM-B (4 programs), CABM-H (2 programs) — with no structural changes. Batches, journal templates, and user accounts are scoped to program_id, not hardcoded to any specific department or program, so each program's batches, templates, and reporting stay independent automatically. Only seed data and the program dropdown's grouping needed updating; no migration, model, or controller redesign was required.

BACKEND (Laravel API)

- Build registration/login/logout controllers on top of Breeze's scaffolded auth (cookie-session mode for web; defer mobile token mode until Phase 7 per your team's decision to address login details as you go)

- Implement role middleware (student / supervisor / coordinator / admin) guarding route groups

- Build admin endpoints: create user, assign role, deactivate account

- Build admin endpoints: create department, create program (seed all 3 departments and 7 programs per the confirmed department coverage)

- Build admin endpoints: create batch (program, coordinator, dates, working days, required hours)

- Auto-create a student_profiles row when a student account is created

WEB (Vue 3)

- Build Admin → User Management page (list, create, edit, deactivate) per the mockup — program dropdown grouped by department now that there are 7 programs across 3 departments

- Build Admin → Departments page

- Build Admin → Batch Management page (create/edit batch) — program dropdown grouped by department

- Wire role-based redirect: each role lands on its own dashboard route after login

MOBILE (React Native / Expo — Student Only)

No mobile work this phase — nothing student-facing is ready to expose yet. Project scaffolding can proceed in parallel if convenient.

DATABASE TABLES TOUCHED

users, student_profiles, departments, programs, batches, batch_students

EXIT CRITERIA — done when:

- An admin can create a department, program, batch, and a student/supervisor/coordinator account end-to-end through the web UI

- Role middleware correctly blocks a student from reaching coordinator/admin routes (and vice versa) when tested manually

- A newly created student account automatically has a corresponding student_profiles row

- All 3 departments (CAST, CABM-B, CABM-H) and all 7 programs are seeded and selectable when creating users and batches

# PHASE 3   Core Daily Journal Flow

Suggested Duration: 2–3 weeks      Depends On: Phase 2

BACKEND (Laravel API)

- Build journal_templates CRUD (coordinator-managed, scoped per program)

- Build journal_entries endpoints: create draft, update draft, submit, fetch by date/range

- Implement entry status state machine: draft → submitted, plus scheduled job to flip submitted-but-late entries to overdue / missing based on batch.daily_reminder_time and working_days_per_week

- Implement the one-entry-per-student-per-day constraint at the application layer (in addition to the DB unique constraint)

WEB (Vue 3)

- Build Write Daily Journal page (dynamic form rendered from the batch's journal_templates.sections)

- Build My Journals (list/history) page

- Build My Journal Calendar page with color-coded statuses (submitted / draft / overdue / missing)

- Build Coordinator → Daily Journal Activities monitoring view (read-only across students in their program)

MOBILE (React Native / Expo — Student Only)

No mobile work this phase — nothing student-facing is ready to expose yet. Project scaffolding can proceed in parallel if convenient.

DATABASE TABLES TOUCHED

journal_templates, journal_entries

EXIT CRITERIA — done when:

- A student can write, save as draft, and submit a daily journal entry through the web UI

- The calendar view correctly reflects entry status using real data, not mock data

- A coordinator can view (but not edit) daily entries across their assigned program

# PHASE 4   Weekly Review Workflow

Suggested Duration: 2 weeks      Depends On: Phase 3

BACKEND (Laravel API)

- Build the scheduled command that bundles the week's journal_entries into a weekly_logs record every Sunday evening, populating weekly_log_entries

- Build supervisor endpoints: list pending weekly logs, approve, return-with-comment

- On return, allow the student to edit underlying entries and resubmit the bundle for re-review

- Write an edit_history record on every submit / edit / return / approve action

WEB (Vue 3)

- Build Student → Weekly Journals page (view bundle status, resubmit after a return)

- Build Supervisor → Review Weekly Journals page (approve / return with comment box)

- Build Supervisor → My Assigned Students page

- Surface edit_history as a visible activity trail on the weekly log detail view

MOBILE (React Native / Expo — Student Only)

No mobile work this phase — nothing student-facing is ready to expose yet. Project scaffolding can proceed in parallel if convenient.

DATABASE TABLES TOUCHED

weekly_logs, weekly_log_entries, edit_history

EXIT CRITERIA — done when:

- The Sunday bundling job runs correctly against a test batch and produces one weekly_logs row per active student

- A supervisor can approve or return a weekly log with a comment, and the student sees that comment

- A returned log can be edited and resubmitted, and each action is recorded in edit_history

# PHASE 5   SIPP Compliance & Reporting

Suggested Duration: 2–3 weeks      Depends On: Phase 2 (Student Info Sheet) and Phase 4 (Weekly Activity Log linkage)

BACKEND (Laravel API)

- Build student_information_sheets endpoints: student submits Section I–III + emergency contact, auto-populated where possible from student_profiles and batch_students

- Build coordinator read-only endpoint for submitted Student Information Sheets

- Build weekly_activity_logs and weekly_activity_entries endpoints (the physical SIPP Weekly Activity Log form, optionally bridged to a weekly_logs record)

- Build sipp_annual_reports generation endpoint (coordinator-triggered, aggregates batch-level data into report_data JSON)

- Build PDF export endpoints for: a date-ranged journal report, the Student Information Sheet, and the Annual SIPP Report

- Build companies, company_supervisors endpoints (HTE hierarchy: Head of Company, Department Head, Supervisor)

WEB (Vue 3)

- Build Student → Student Info Sheet page (form + submission status)

- Build Student → Generate Report page (date range picker, PDF download)

- Build Coordinator → Student Info Sheets, Annual SIPP Report, and Partner Companies pages

- Build Admin → Companies, Student Info Sheet, and Annual SIPP Report pages

MOBILE (React Native / Expo — Student Only)

No mobile work this phase — nothing student-facing is ready to expose yet. Project scaffolding can proceed in parallel if convenient.

DATABASE TABLES TOUCHED

student_information_sheets, weekly_activity_logs, weekly_activity_entries, sipp_annual_reports, companies, company_supervisors

EXIT CRITERIA — done when:

- A student can submit a complete Student Information Sheet and a coordinator can view it read-only

- A coordinator can generate an Annual SIPP Report for a batch and export it as a PDF

- A student can export a date-ranged journal report as a PDF that matches what's in the system

# PHASE 6   Notifications & Administrative Tools

Suggested Duration: 2 weeks      Depends On: Phase 3 (entries to notify about) and Phase 2 (admin shell)

BACKEND (Laravel API)

- Build the scheduled command that scans for missing/overdue entries at the batch's daily_reminder_time and writes notifications rows

- Build email delivery (Mailtrap in dev) for the daily reminder

- Build push notification delivery hook for mobile (payload only — actual device delivery wired in Phase 7 alongside the mobile app)

- Build system_settings endpoints (get/update key-value settings) backing the System Settings page

- Build system_logs writer: hook into key actions (login, account changes, batch changes, approvals, scheduled jobs) to write audit entries

- Build coordinator overdue/missing tracking endpoint (list of interns with pending entries, scoped to their program)

WEB (Vue 3)

- Build Admin → System Settings page (general, notification, and journal settings)

- Build Admin → Audit Logs page (filterable by action, user role, date)

- Wire the Coordinator dashboard's overdue/missing panel to real data

- Build in-app notification indicator (bell icon / badge) reading from the notifications table

MOBILE (React Native / Expo — Student Only)

No mobile work this phase — nothing student-facing is ready to expose yet. Project scaffolding can proceed in parallel if convenient.

DATABASE TABLES TOUCHED

notifications, system_settings, system_logs

EXIT CRITERIA — done when:

- A test student with a missing entry receives an email reminder at the configured time

- Changing a setting in System Settings (e.g. reminder time) actually changes the scheduled job's behavior

- Audit Logs shows real entries for logins, approvals, and admin actions, not placeholder data

# PHASE 7   Mobile Parity, Polish & Testing

Suggested Duration: 2–3 weeks      Depends On: Phases 2–6 (mobile only needs the student-facing slice of each)

BACKEND (Laravel API)

- Implement mobile login/token issuance on the existing auth endpoints (token-based Sanctum auth, scoped to student-only abilities, per your team's planned approach)

- Implement token revocation on mobile logout (revoke only the device's token, not all of the student's sessions)

- Wire push notification delivery (Expo push service) using the payloads built in Phase 6

- Final API hardening pass: form request validation review, authorization policy review per role, rate limiting on auth endpoints

WEB (Vue 3)

- Cross-browser and responsive QA across the four role dashboards

- Replace any remaining mockup placeholder data with live API data

- Accessibility and empty-state pass (no data, loading, and error states for every list/table)

MOBILE (React Native / Expo — Student Only)

- Scaffold the Expo project in mobile/ (if not already done in Phase 1) with Expo Router

- Implement secure token storage via expo-secure-store

- Build student-only screens: login, dashboard, journal calendar, write daily journal, my journals, weekly journals, generate report, student info sheet

- Wire expo-notifications for missing/overdue push alerts

- Device testing on at least one Android and one iOS device or emulator

DATABASE TABLES TOUCHED

No new tables — this phase consumes everything built in Phases 2–6

EXIT CRITERIA — done when:

- A student can log in, write and submit a journal entry, view their calendar, and receive a push notification from the mobile app

- Logging out on one device does not log out the student's session on another device

- Full user acceptance testing completed with at least one user per role (student, supervisor, coordinator, admin)

- System is stable enough for capstone defense walkthrough across all three platforms